## Project_Daily_Status
Ecommerce app
DATE | DAY | Activities | Completion Status (%) | Remarks
2020-06-16 | Tuesday | Project Discussion and Gathering Ideas | 5% | Each one of us gave opinions and ideas for the project.
2020-06-17 | Wednesday | Discussing Features and Preparing SRS | 15% | Everyone discussed the requirements and how to go about the project.
2020-06-18 | Thursday | Again a meeting for ideas and discussing about the project. | 20% | Finalising the approach and strategy for the project
2020-06-19 | Friday | Started working on the SRS | 25% | Everyone work was on the correct track.
2020-06-20 | Saturday | Tasks got distributed which included UI, table schema, SRS, Data Collection | 40% | The load of work for the project got increased.
2020-06-21 | Sunday | We worked upon the UI and tables needed for the project. | 55% | The load of work for the project got increased even more.
2020-06-22 | Monday | Backend coding, signup forms, diagrams and SRS | 60% | Errors and glitches started to trouble everyone.
2020-06-22 | Monday | Backend coding, signup forms, diagrams and SRS | 60% | Errors and glitches increased as the project had multiple aspects and scenarios.
2020-06-23 | Tuesday | Worked on admin panel, worked on best-coding practices and table schema | 65% | Tried our best to solve every error and issue.
2020-06-24 | Wednesday | Started working on videos, images and banners for products. Admin panel and data collection were also done. | 70% | Multiple corrections and choosing was done for the contents and pictures.
2020-06-25 | Thursday | Implemented videos using bootstrap, CRUD operations on tables, and paytm integration. | 75% | A day full of coding .
2020-06-26 | Friday | Navbars and dropdown list were integrated and done displaying for the same. | 78% | Glitches introduced once again.
2020-06-27 | Saturday | Jsp pages and displaying were done for the products. | 80% | Everything is well positioned.
2020-06-28 | Sunday | Slight changes in the posters, logo and navbars and testing was done | 85% | Put our best for the project.
2020-06-29 | Monday | Checkout page, email and pdf send program, and final documentation | 87% | Everything is well positioned.
2020-06-30 | Tuesday | Checkout page, email and pdf send program, and final documentation | 89% | Everything is well positioned.
2020-07-01 | Wednesday | Add to cart logic, orders, filters,documentation, email send program | 92% | Everything is well positioned.
2020-07-02 | Thursday | Order and cart UI, filters,documentation | 93% | Everything is well positioned.
2020-07-03 | Friday | Order operations,documentation, jsp pages | 94% | Everything is well positioned.
2020-07-04 | Saturday | User update profile, frontend Ajax, documentation, pdf files, product images | 97% | Everything is well positioned.
2020-07-05 | Sunday | Minor issues fixed, documentation, best coding practices, product images | 99% | Everything is well positioned.
2020-07-06 | Monday | The project is ready. | 100% | Everything is well positioned and working fine.

## Project_TimeLine
SNO | Milestone | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Remarks
1 | SRS | 2020-06-17 | 2020-06-22 | 2020-06-17 | 2020-07-02 | Completed
2 | Data Collection | 2020-06-17 | 2020-06-19 | 2020-06-17 | 2020-06-25 | Completed
3 | Backend coding | 2020-06-17 | 2020-06-25 | 2020-06-19 | 2020-07-05 | Completed
4 | Frontend coding | 2020-06-17 | 2020-06-26 | 2020-06-18 | 2020-07-04 | Completed
5 | Banners and pictures | 2020-06-19 | 2020-06-22 | 2020-06-19 | 2020-06-28 | Completed
6 | Testing | 2020-06-26 | 2020-06-30 | 2020-06-28 | 2020-07-05 | Completed