## Sheet1
Ecommerce App
DATE | DAY | Akshat Singh | Rishabh Kumar Singh | Raghavendra Singh Bhati | Devyanshu Arora | Remarks(if any)
2020-06-16 | Tuesday | Project Discussion | Project Discussion | Project Discussion | Project Discussion and Gathering Ideas | Project Discussion and Gathering Ideas
|  | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress
2020-06-17 | Wednesday | Preparing SRS | Preparing SRS | Preparing SRS | Preparing SRS and Discussing Features | Preparing SRS and Discussing Features
|  | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress
2020-06-18 | Thursday | Gathering Ideas | Gathering Ideas and working on SRS | Gathering Ideas and working on SRS | Gathering and searching ideas | A lot of ideas
|  | Completed | In-Progress | In-Progress | In-Progress
2020-06-19 | Friday | Preparing SRS | Preparing SRS | Preparing SRS | Preparing SRS | SRS design and templates
|  | In-Progress | In-Progress | In-Progress | In-Progress
2020-06-20 | Saturday | Table Schema | Working on logo, UI and SRS | Tables | Gathering products information | Everyone worked fine.
|  | In-Progress | In-Progress | In-Progress | In-Progress
2020-06-21 | Sunday | Table Schema | Table Schema and report | Working on signup forms(javascript) | Gathering products information | Everyone worked fine.
|  | In-Progress | In-Progress | In-Progress | In-Progress
2020-06-22 | Monday | User table backend | Working on diagrams and SRS | Working on signup forms(javascript) | Gathering products information and prepared SRS | Everyone worked fine.
|  | Completed | Completed | In-Progress | In-Progress
2020-06-23 | Tuesday | User Profile and admin panel | Editing and testing codes for the app | Working on signup forms(javascript) | Data Collection | Everyone worked fine.
|  | In-Progress | Completed | Completed | In-Progress
2020-06-24 | Wednesday | Admin Panel | Searched banners and advertisements for the website and added them | PayTm integration | Data Collection | Everyone worked fine.
|  | Completed | In-Progress | In-progress | In-Progress
2020-06-25 | Thursday | UI and product table CRUD operations | Searched banners and advertisements for the website and added them | PayTm integration | Data Collection | Everyone worked fine.
|  | Completed | Completed | Completed | Completed
2020-06-26 | Friday | Searching and displaying products | Added videos and banners using bootstrap | Welcome and acknowledgement mail | Adding products using js | Everyone worked fine.
|  | Completed | Completed | In-Progress | In-Progress
2020-06-27 | Saturday | Delete product and add reviews | Made error pages using css and designed the logo. | email send program | Adding products using js | Everyone worked fine.
|  | Completed | Completed | In-Progress | In-Progress
2020-06-28 | Sunday | Add products servlets | Made error pages using css and designed the logo. | email send program | Adding products using js | Everyone worked fine.
|  | In-Progress | Completed | In-Progress | Completed
2020-06-29 | Monday | Checkout page and add to cart | Made register page using js and css for auto preview of profile picture. | email send program | Using Filters | Everyone worked fine.
|  | In-Progress | Completed | In-Progress | In-Progress
2020-06-30 | Tuesday | Checkout page and add to cart | Contents and ideas for the ppt | email send program | Using Filters | Everyone worked fine.
|  | Completed | Completed | In-Progress | In-Progress
2020-07-01 | Wednesday | Add to cart logic and orders save and paytm integrate | Documentation, charts and ppt | email and pdf send program | Using Filters | Everyone worked fine.
|  | In-Progress | In-Progress | Completed | In-Progress
2020-07-02 | Thursday | Order and cart UI | Documentation,charts and ppt | Worked on filters(admin,checkout,validate) | Worked on filters | Everyone worked fine.
|  | Completed | In-Progress | Completed | Completed
2020-06-03 | Friday | User order operations | Documentation,charts and ppt | Worked on jsp pages(updateprofile, userprofile) and some product images | No-work due to visit to SNU | Everyone worked fine.
|  | Completed | In-Progress | Completed | -
2020-06-04 | Saturday | User update and profile. Front end ajax work and saving details of user cart after logout | Documentation,charts and ppt | Fixed some errors in pdf file and product images | Worked on admin dashboard | Everyone worked fine.
|  | Completed | In-Progress | Completed | Completed
2020-06-05 | Sunday | Worked on minor backend issues | Documentation of 18 java files and ppt | Documentation of 14 java files and product images | Added comments in files and multiple photos for the products | Everyone worked fine.
|  | Completed | Completed | Completed | Completed